500 Workers Initiative 
Jurisdictional high-level status as at 31 May 2026

Notes:

  - Data is as at 31 May 2026 and is subject to regular changes.

  - Due to individual jurisdictional contractual arrangements with service providers already in place, not all state and territory data is updated monthly.

  - States and territories have requirements to receive Commonwealth funding including annual reporting obligations to the Commonwealth under the Family, Domestic and Sexual Violence Responses 2021-30 Federation Funding Agreement.

  - Use of the word ‘commenced’ in the below table means workers who have started in their roles and are working with victim-survivors.

  - The 500 Workers Initiative has a phased approach, with 352.43 full-time equivalent (FTE) workers committed to by 30 June 2024, 462.61 FTE workers by 30 June 2025 and 500 FTE workers by 30 June 2026.

| Jurisdiction | Commenced Workers | Commenced FTE | Next Steps |
| --- | --- | --- | --- |
| New South Wales (NSW) | 159 | 146.4 | The recruitment of new workers is progressing in line with NSW’s plan: - NSW has awarded contracts to 82 service providers to deliver 148.4 FTE. - 159 workers (146.4 FTE) are now delivering domestic, family and sexual violence services (DFSV) across NSW. - The remaining 2024-25 quota have recruitment activity underway (2 FTE). - NSW is working with service providers to support recruitment for the remaining 2 FTE. |
| Victoria | 107 | 101 | - Victoria has now met its total target under the 500 Workers Initiative, with 107 new workers recruited, equating to 101 FTE under two tranches. - Tranche 1 is complete with 65 people (total 59 FTE) recruited. - Victoria has now recruited 42 workers (total 42 FTE) for Tranche 2. - The filled roles include: - 20 case managers at multicultural agencies. Collectively, they speak Mandarin, Cantonese, Tamil, Hindi, Urdu, Arabic, Ukrainian and Russian, as well as all speaking English. 3 workers employed at an Aboriginal Community Controlled Organisation. |
| Queensland | 131 | 112 | Queensland has now allocated all funding and FTE and has over-delivered on its target of 111.6 FTE, with funding allocated for a total of 113 FTE workers. |
| Western Australia (WA) | 50 | 50 | Western Australia has successfully completed its recruitment plan with 50 FTE employed across 13 organisations in metropolitan, regional and remote areas of the State. |
| South Australia | 49 | 36.8 | South Australia has now met its total target under the 500 Workers Initiative, with 36.8 FTE commenced, equivalent to 49 workers across 36 services. |
| Tasmania | 33 | 24.6 | Tasmania has now met its total 500 Workers Initiative target of 24.6 FTE commenced workers across 13 services. |
| Australian Capital Territory (ACT) | 8 | 7.6 | The ACT has delivered its total 500 Workers Initiative FTE target of 7.6 FTE. 4 workers (4.0 FTE) have commenced with Canberra Rape Crisis Centre. 2 workers (2.0 FTE) have commenced with YWCA. 1 worker (1.0 FTE) has commenced with Multicultural Hub. 1 worker (0.6 FTE) has commenced with Domestic Violence Crisis Service. |
| Northern Territory | 20 | 19.6 | Recruitment has increased with 20 commenced workers, including: - 12 (11.6 FTE) Children’s safety workers - 3 FTE non legal support workers, and 5 FTE co-responder pilot victim-survivor case manager |
| TOTAL | 557 | 498 |  |